## Instructions
Overview
This workbook provides a product backlog template as well as a 1-week and 2-week sprint backlog template. Select the sprint backlog template for your sprint length and then delete the other. Below are instructions on how to use each template, including which fields are editable, which are not, and issues to be aware of as you make modifications.
Product Backlog Instructions
Note: The product backlog template uses conditional formatting rather than visual basic (VBA) programming to avoid the use of macros in the Excel file, which can be problematic for some users in certain environments. The product backlog template options provide the data and calculations to not only generate a project/release burndown chart, but also to provide empirical "PERT" extrapolations for release delivery dates based on a scrum team's velocity. The template highlights all rows within the ranges calculated in columns K, L and M. Extrapolation data is calculated in the range F2:M15, and assumes a project with 10 sprints. This can be modified, but remember that the burndown chart's data range must be manually updated to match any changes. "P" stands for "pessimistic" (i.e. lowest velocity), "ML" stands for "most likely" (i.e. average velocity"), and "O" stands for "optimistic" (i.e. highest velocity). Be aware that many cells contain values and/or formulas required to calculate other cells and/or the burndown chart. Comments are provided in each cell (or the first cell in a range) that requires manual updating by the user. Avoid changing values in any cells that do not have a red flag in the upper right corner, indicating there is a comment.
Sprint Backlog Instructions
The sprint backlog templates provide the data and calculations to automatically generate a sprint burndown chart for both story points and task hours. For instructions, see https://platinumedge.com/blog/anatomy-sprint-backlog. The two template options are identical, except for sprint length. Burndown chart data is generated based on data in rows 81-84. Rows can be deleted or added for tasks in each user story, however be aware that formulas in rows 81-84 may have to be updated as well as in each individual user story row. Be aware that many cells contain values and/or formulas required to calculate other cells and/or the burndown chart. Avoid changing values in any cells that contain formulas.

## Product Backlog
ArcStat |  |  | Requirement |  | Empirical PERT Calculations |  |  |  |  | P Scope | ML Scope | O Scope
|  |  | Improvement |  |  | Actual | Sprints | Actual | Plan | Remain | Remain | Remain
2021-03-15 | Project start |  | Maintenance |  | Sprint | Velocity | Remain | Burn | Burn | 10 | 10 | 10
7 | Sprint length (days) |  | Overhead |  | Start | 10 | 10 | 23 | 23 | 100 | 100 | 100
1 | Release 1 sprints (#) |  |  |  | 1 |  | 9 | 23 | 20.7 | 90 | 90 | 90
11 | Release 1 release sprint length (days) |  |  |  | 2 |  | 8 | 23 | 18.4 | 80 | 80 | 80
2021-03-26 | Release 1 date |  |  |  | 3 |  | 7 | 23 | 16.1 | 70 | 70 | 70
2 | Release 2 sprints (#) |  |  |  | 4 |  | 6 | 23 | 13.8 | 60 | 60 | 60
14 | Release 2 release sprint length (days) |  |  |  | 5 |  | 5 | 23 | 11.5 | 50 | 50 | 50
2021-04-09 | Release 2 date |  |  |  | 6 |  | 4 | 23 | 9.2 | 40 | 40 | 40
2 | Release 3 sprints (#) |  |  |  | 7 |  | 3 | 23 | 6.9 | 30 | 30 | 30
17 | Release 3 release sprint length (days) |  |  |  | 8 |  | 2 | 23 | 4.6 | 20 | 20 | 20
2021-04-26 | Release 3 date |  |  |  | 9 |  | 1 | 23 | 2.3 | 10 | 10 | 10
[5 empty] | 10 |  | 0 | 23 | 0 | 0 | 0 | 0
ArcStat Product Backlog | [5 empty] | Running | Sprint | Release | Release
ID | Title | Description | Acceptance Criteria | Type | Size | Total | Completed | Dates | Goals
2 | main menu | As a user, I want selection of tests so that I know what the tool can help me with. | When I do this: open the tool, this happens:prompts for the different main options appear. | Requirement | 1 | 1
3 | Field name selection | As a user, I want to select field names so that statistical analysis can be done on the selected fields. |  | Requirement | 1 | 2
4 | Analysis type selection | As a user, I want to select the type of statistical analysis I want to conduct. | A wide selection for the user is integrated | Requirement | 1 | 3
5 | Graph type selection | As a user, I want to select the graph type I need. | A graph is produced | Requirement | 1 | 4
1 | Output | As a user, I want to output results to a csv so that I can use results other places | a csv is produced and prompts the user for an outpur location | Requirement | 1 | 5
6 | Release 1 |  |  | Overhead | 0 | 5 |  | 2021-03-26 | Release 1: <Basic interface and function complete>
7 | Raster Analysis Functionality | Build in internal functionality to handle raster data | Raster data can be meaningfully interpreted by the program | Overhead | 2 | 7
8 | Raster correlation with Vector | As a user, I want to be able to do analysis between a vector dataset and a raster dataset | Meaningful (and correct) analysis can be drawn from a given vector and raster dataset | Requirement | 5 | 12
9 | correlation | As a user, I want to do multi-field analysis | when at least 3 correlation tests are implemented | Improvement | 2 | 14
10 | interactive | As a user, I want to be able to interact with output | interactivly change graph axis names and scale | Improvement | 2 | 16 |  | 2021-04-09 | Release 2: <All function created>
11 | Release 2 |  |  | Overhead | 1 | 17
13 | Interface Improvement |  |  | Improvement | 1 | 18
15 | Code Error |  |  | Requirement | 1 | 19
14 | help boxes |  |  | Requirement | 1 | 20
16 | Metadata |  |  | Requirement | 1 | 21
20 | User Manual |  |  | Overhead | 1 | 22
19 | Final Presentation |  |  | Overhead | 1 | 23 |  | 2021-04-26 | Release 3: <Polished and complete>
17 | <PBI title> |  |  |  |  | 23
18 | <PBI title> |  |  |  |  | 23
24 | <PBI title> |  |  |  | 21 | #REF!
25 | <PBI title> |  |  |  | 34 | #REF!
26 | <PBI title> |  |  |  | 13 | #REF!
27 | <PBI title> |  |  |  | 55 | #REF!
28 | <PBI title> |  |  |  | 89 | #REF!
29 | <PBI title> |  |  |  | 55 | #REF!
30 | <PBI title> |  |  |  | 34 | #REF!
31 | <PBI title> |  |  |  | 55 | #REF!
32 | <PBI title> |  |  |  | 21 | #REF!
34 | <PBI title> |  |  |  | 13 | #REF!
35 | <PBI title> |  |  |  | 55 | #REF!
36 | <PBI title> |  |  |  | 144 | #REF!
Note on A2: Instructions: Update the portion in <> with your product's name.
Note on A4: Instructions (not required): Insert the project start date.
Note on A5: Instructions (not required): Enter the sprint length, in multiples of 7 days per week of sprint.
Note on G5: Instructions: Enter the scrum team's conservative estimate of how many story points they think they can accomplish the first sprint. This cell will be ignored as soon as there is actual velocity data from the first sprint.
Note on I5: Instructions: If the product owner has a target point in the product backlog, update this cell to point to the cell in column G of the last backlog item included in the scope of the project. (This template provides an example of how you would point to PBI 0018, if that were the target.)
Note on A6: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A7: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A9: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A10: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A12: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A13: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A18: Instructions: Update the portion in <> with your product's name.
Note on A19: Instructions: Enter the ID of the product backlog item (PBI). The ID usually reflects when it was entered in the system, not the priority. The order of the PBIs indicates the priority. This applies to all cells in this column.
Note on B19: Instructions: Enter the title of the product backlog item. Applies to all cells in this column.
Note on C19: Instructions: Enter the product backlog item description. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on D19: Instructions: Enter the product backlog item acceptance criteria. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on E19: Instructions: Select what type of product backlog item this is (Applies to all cells in this column): Requirement: Typically a user story--work that needs to be done to generate functionality for the user. Improvement: Action items from the sprint retrospective. Maintenance: Development work that neesd to be done on the system, but doesn't create new functionality.. Overhead: Non-development work that needs to be done, but doesn't add direct value to the user.
Note on F19: Instructions: Enter the Fibonacci size estimate assigned by the development team. Applies to all cells in this column.
Note on H19: Instructions: Enter the number of the sprint when the PBI was completed (done).Enter whole numbers to match the format of what appears in F6:F15 above. Applies to all cells in this column.
Note on I19: Instructions (optional): Update any cell below to point to the date generated in A4:A14 indicating the projected release date. Note: This may change as velocity changes.
Note on J19: Instructions (optional): Update <> with the actual release goal.

## Sprint Backlog - 1 week option
<Product name> - Sprint <#>
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>
[6 empty] | Available working hours in the sprint |  |  |  | Days in sprint: | 4.5
Sprint Goal | [6 empty] | M | Tu | W | Th | F | Total
Demonstrate the ability to <sprint goal>. (NOTE: Define a sprint goal in terms of working customer functionality you will be able to demonstrate to internal stakeholders and possibly release to the marketplace.) | [5 empty] | Developers | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Review + Retrospective
[6 empty] | <Developer name> | 4 | 6 | 6 | 6 | 4 | 26
[6 empty] | <Developer name> | 4 | 6 | 6 | 6 | 4 | 26
[6 empty] | <Developer name> | 4 | 6 | 6 | 6 | 4 | 26
[6 empty] | <Developer name> | 4 | 6 | 6 | 6 | 4 | 26
[6 empty] | <Developer name> | 4 | 6 | 6 | 6 | 4 | 26
[11 empty] | Total sprint hours: | 130
[11 empty] | Total per day: | 28.8889
Feature Burndown - Based on estimated hours remaining
[7 empty] | M | Tu | W | Th | F
ID | Task | Description | Acceptance Criteria | Type | Story Points | Responsible | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Review + Retrospective | Done (Y) | Accepted (Y/N)
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 8 | Developer name | 8 | 8 | 8 | 8 | 8
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 5 | Developer name | 5 | 5 | 5 | 5 | 5
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 3 | Developer name | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 2 | Developer name | 2 | 2 | 2 | 2 | 2
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 1 | Developer name | 1 | 1 | 1 | 1 | 1
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 3 | 3 | 3 | 3 | 3
Actual Hrs Remaining | [6 empty] | 120 | 120 | 120 | 120 | 120
Schedule Hrs Remaining | [6 empty] | 130 | 97.5 | 65 | 32.5 | 0
Story Points Remaining | [6 empty] | 19 | 19 | 19 | 19 | 19
[6 empty] | Day: | 1 | 2 | 3 | 4 | 5
Issues
Team Member
<issue>
Team Member
<issue>
<issue>

## Sprint Backlog - 2 week option
<Product name> - Sprint <#>
Sprint Dates: <Month> <DD> - <Month> <DD>, <YYYY>
[6 empty] | Available working hours in the sprint |  |  |  | Days in sprint: | 9
Sprint Goal | [6 empty] | M | Tu | W | Th | F | M | T | W | Th | F | Total
Demonstrate the ability to <sprint goal>. (NOTE: Define a sprint goal in terms of working customer functionality you will be able to demonstrate to internal stakeholders and possibly release to the marketplace.) | [5 empty] | Developers | <DD> Sprint Planning | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> Sprint Review + Retrospective
[6 empty] | <Developer name> | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 52
[6 empty] | <Developer name> | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 52
[6 empty] | <Developer name> | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 52
[6 empty] | <Developer name> | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 52
[6 empty] | <Developer name> | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 52
[16 empty] | Total sprint hours: | 260
[16 empty] | Total per day: | 28.8889
Feature Burndown - Based on estimated hours remaining
[7 empty] | M | Tu | W | Th | F | M | T | W | Th | F
ID | Task |  |  | Type | Story Points | Responsible | <DD> Sprint Planning | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> | <DD> Sprint Review + Retrospective | Done (Y) | Accepted (Y/N)
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 8 | Developer name | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 5 | Developer name | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 3 | Developer name | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 2 | Developer name | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
#### | <User story title> | As a ____, I want to ____, so that ____. | When I do this: ____, this happens:____. | Requirement | 1 | Developer name | bar: M to F
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| <task> | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Actual Hrs Remaining | [6 empty] | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
Schedule Hrs Remaining | [6 empty] | 260 | 231.1111 | 202.2222 | 173.3333 | 144.4444 | 115.5556 | 86.6667 | 57.7778 | 28.8889 | 2.1316e-14
Story Points Remaining | [6 empty] | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
[6 empty] | Day: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Issues
Team Member
<issue>
Team Member
<issue>
<issue>